## Sheet1
Name | Code | Project Name | Project Id | Project Code | Description | Workflow | Priority | Parent Task | Start Date | Target Date | Actual Start Date | Actual End Date | Lagged Days | Workflow Status | Review Status | Review Id | Predecessor | Progress | Allocator | Version
Architecture | 529D0266-26AF-F011-A460-7C70DB2D7E2B | JKR Workshop | 19 | JKR-001 | PT0H0M0S | 1s-Rw-WF | High | Good For Construction | 2025-10-22 | 2026-02-10 | 2025-10-20 | 2026-01-26 | 0 | Open | Open | 30 |  |  | SuperAdmin
BASEMENT | DCFC505D-25AF-F011-A460-7C70DB2D7E2B | JKR Workshop | 19 | JKR-001 | PT0H0M0S |  |  | SUPERSTRUCTURE | 2026-04-02 | 2026-06-16 | 2026-03-18 | 2026-05-28 | 0 | [5 empty] | SuperAdmin
A100-Parking Deck Floor Plan | F9448135-26AF-F011-A460-7C70DB2D7E2B | JKR Workshop | 19 | JKR-001 | Design approval for A100-Parking Deck Floor Plan | 1s-Rw-WF | High | Architecture | 2025-10-22 | 2025-11-04 | 2025-10-20 | 2025-10-29 | 43 | Open | Open | 30 |  |  | SuperAdmin
A101-First Floor Plan | F8448135-26AF-F011-A460-7C70DB2D7E2B | JKR Workshop | 19 | JKR-001 | Design approval for A101-First Floor Plan | 1s-Rw-WF | High | Architecture | 2025-11-05 | 2025-11-18 | 2025-10-30 | 2025-11-11 | 33 | Open | Open | 30 | 378FS |  | SuperAdmin
A102-Second Floor Plan | F7C78B00-26AF-F011-A460-7C70DB2D7E2B | JKR Workshop | 19 | JKR-001 | Design Approval for A102-Second Floor Plan | 1s-Rw-WF | High | Architecture | 2025-11-19 | 2025-12-02 | 2025-11-12 | 2025-11-24 | 23 | Open | Open | 30 | 379FS |  | SuperAdmin
A103-Third Floor Plan | F6C78B00-26AF-F011-A460-7C70DB2D7E2B | JKR Workshop | 19 | JKR-001 | Design approval for A103-Third Floor Plan | 1s-Rw-WF | High | Architecture | 2025-12-03 | 2025-12-16 | 2025-11-25 | 2025-12-07 | 13 | Open | Open | 30 | 380FS |  | SuperAdmin
A104-Fourth Floor Plan | F5C78B00-26AF-F011-A460-7C70DB2D7E2B | JKR Workshop | 19 | JKR-001 | Design approval for A104-Fourth Floor Plan | 1s-Rw-WF | High | Architecture | 2025-12-17 | 2025-12-30 | 2025-12-08 | 2025-12-17 | 3 | Open | Open | 30 | 381FS |  | SuperAdmin
A105-Fifth Floor Plan | 6C28D362-27AF-F011-A460-7C70DB2D7E2B | JKR Workshop | 19 | JKR-001 | Design Approval for A105-Fifth Floor Plan | 3s-Rw-WF | High | Architecture | 2025-12-31 | 2026-01-13 | 2025-12-18 | 2025-12-30 | 0 | Open | Open | 31 | 382FS |  | SuperAdmin
A106-Green Roof | 6B28D362-27AF-F011-A460-7C70DB2D7E2B | JKR Workshop | 19 | JKR-001 | Design Approval for A106-Green Roof | 3s-Rw-WF | High | Architecture | 2026-01-14 | 2026-01-27 | 2026-01-01 | 2026-01-13 | 0 | Open | Open | 31 | 383FS |  | SuperAdmin
A107-Roof Plan | 6A28D362-27AF-F011-A460-7C70DB2D7E2B | JKR Workshop | 19 | JKR-001 | Design Approval for A107-Roof Plan | 3s-Rw-WF | High | Architecture | 2026-01-28 | 2026-02-10 | 2026-01-14 | 2026-01-26 | 0 | Open | Open | 31 | 384FS |  | SuperAdmin
Beam Concreting -Phase I | EAFC505D-25AF-F011-A460-7C70DB2D7E2B | JKR Workshop | 19 | JKR-001 | PT0H0M0S |  |  | GROUND FLOOR | 2026-06-17 | 2026-06-29 | 2026-05-31 | 2026-06-09 | 0 |  |  |  | 394FS |  | SuperAdmin
Beam Concreting - Phase II | ECFC505D-25AF-F011-A460-7C70DB2D7E2B | JKR Workshop | 19 | JKR-001 | PT0H0M0S |  |  | GROUND FLOOR | 2026-06-30 | 2026-07-13 | 2026-06-10 | 2026-06-22 | 0 |  |  |  | 396FS |  | SuperAdmin
Column Concreting - Phase I | F2FC505D-25AF-F011-A460-7C70DB2D7E2B | JKR Workshop | 19 | JKR-001 | PT0H0M0S |  |  | GROUND FLOOR | 2026-08-11 | 2026-08-21 | 2026-07-15 | 2026-07-23 | 0 |  |  |  | 399FS |  | SuperAdmin
Column Concreting - Phase II | F4FC505D-25AF-F011-A460-7C70DB2D7E2B | JKR Workshop | 19 | JKR-001 | PT0H0M0S |  |  | GROUND FLOOR | 2026-08-24 | 2026-08-31 | 2026-07-26 | 2026-08-02 | 0 |  |  |  | 400FS |  | SuperAdmin
Beam Concreting - Phase I | FAFC505D-25AF-F011-A460-7C70DB2D7E2B | JKR Workshop | 19 | JKR-001 | PT0H0M0S |  |  | FIRST FLOOR | 2026-09-01 | 2026-09-10 | 2026-08-03 | 2026-08-11 | 0 |  |  |  | 401FS |  | SuperAdmin
Beam Concreting - Phase II | FCFC505D-25AF-F011-A460-7C70DB2D7E2B | JKR Workshop | 19 | JKR-001 | PT0H0M0S |  |  | FIRST FLOOR | 2026-09-11 | 2026-09-24 | 2026-08-06 | 2026-08-19 | 0 |  |  |  | 402FS |  | SuperAdmin
Column Concreting - Phase I | 02FD505D-25AF-F011-A460-7C70DB2D7E2B | JKR Workshop | 19 | JKR-001 | PT0H0M0S |  |  | FIRST FLOOR | 2026-10-23 | 2026-11-04 | 2026-09-16 | 2026-09-24 | 0 |  |  |  | 406FS |  | SuperAdmin
Column Concreting - Phase II | 04FD505D-25AF-F011-A460-7C70DB2D7E2B | JKR Workshop | 19 | JKR-001 | PT0H0M0S |  |  | FIRST FLOOR | 2026-11-05 | 2026-11-16 | 2026-09-27 | 2026-10-05 | 0 |  |  |  | 407FS |  | SuperAdmin
Beam Concreting -Phase I | 0AFD505D-25AF-F011-A460-7C70DB2D7E2B | JKR Workshop | 19 | JKR-001 | PT0H0M0S |  |  | SECOND FLOOR | 2026-11-27 | 2026-12-09 | 2026-10-06 | 2026-10-18 | 0 |  |  |  | 409FS |  | SuperAdmin
Beam Concreting - Phase II | 0CFD505D-25AF-F011-A460-7C70DB2D7E2B | JKR Workshop | 19 | JKR-001 | PT0H0M0S |  |  | SECOND FLOOR | 2026-12-10 | 2026-12-23 | 2026-10-19 | 2026-10-29 | 0 |  |  |  | 410FS |  | SuperAdmin
Column Concreting - Phase I | 12FD505D-25AF-F011-A460-7C70DB2D7E2B | JKR Workshop | 19 | JKR-001 | PT0H0M0S |  |  | SECOND FLOOR | 2027-01-14 | 2027-01-26 | 2026-11-18 | 2026-11-30 | 0 |  |  |  | 413FS |  | SuperAdmin
Column Concreting - Phase II | 14FD505D-25AF-F011-A460-7C70DB2D7E2B | JKR Workshop | 19 | JKR-001 | PT0H0M0S |  |  | SECOND FLOOR | 2027-01-27 | 2027-02-04 | 2026-12-01 | 2026-12-09 | 0 |  |  |  | 414FS |  | SuperAdmin
Beam Concreting -Phase I | 1AFD505D-25AF-F011-A460-7C70DB2D7E2B | JKR Workshop | 19 | JKR-001 | PT0H0M0S |  |  | THIRD FLOOR | 2027-02-05 | 2027-02-16 | 2026-12-10 | 2026-12-20 | 0 |  |  |  | 415FS |  | SuperAdmin
Beam Concreting - Phase II | 1CFD505D-25AF-F011-A460-7C70DB2D7E2B | JKR Workshop | 19 | JKR-001 | PT0H0M0S |  |  | THIRD FLOOR | 2027-02-17 | 2027-03-02 | 2026-12-21 | 2027-01-04 | 0 |  |  |  | 417FS |  | SuperAdmin
Column Concreting - Phase I | 22FD505D-25AF-F011-A460-7C70DB2D7E2B | JKR Workshop | 19 | JKR-001 | PT0H0M0S |  |  | THIRD FLOOR | 2027-03-24 | 2027-04-05 | 2027-01-24 | 2027-02-02 | 0 |  |  |  | 420FS |  | SuperAdmin
Column Concreting - Phase II | 24FD505D-25AF-F011-A460-7C70DB2D7E2B | JKR Workshop | 19 | JKR-001 | PT0H0M0S |  |  | THIRD FLOOR | 2027-04-06 | 2027-04-14 | 2027-02-03 | 2027-02-11 | 0 |  |  |  | 421FS |  | SuperAdmin
Beam Concreting -Phase I | 2AFD505D-25AF-F011-A460-7C70DB2D7E2B | JKR Workshop | 19 | JKR-001 | PT0H0M0S |  |  | FOURTH FLOOR | 2027-04-15 | 2027-04-26 | 2027-02-11 | 2027-02-11 | 0 |  |  |  | 422FS |  | SuperAdmin
Beam Concreting - Phase II | 2CFD505D-25AF-F011-A460-7C70DB2D7E2B | JKR Workshop | 19 | JKR-001 | PT0H0M0S |  |  | FOURTH FLOOR | 2027-04-27 | 2027-05-10 | 2027-02-14 | 2027-02-25 | 0 |  |  |  | 424FS |  | SuperAdmin
Column Concreting - Phase I | 32FD505D-25AF-F011-A460-7C70DB2D7E2B | JKR Workshop | 19 | JKR-001 | PT0H0M0S |  |  | FOURTH FLOOR | 2027-06-01 | 2027-06-11 | 2027-03-18 | 2027-03-31 | 0 |  |  |  | 427FS |  | SuperAdmin
Beam Concreting -Phase I | 3AFD505D-25AF-F011-A460-7C70DB2D7E2B | JKR Workshop | 19 | JKR-001 | PT0H0M0S |  |  | FIFTH FLOOR | 2027-06-23 | 2027-07-02 | 2027-04-08 | 2027-04-19 | 0 |  |  |  | 429FS |  | SuperAdmin
Beam Concreting - Phase II | 3CFD505D-25AF-F011-A460-7C70DB2D7E2B | JKR Workshop | 19 | JKR-001 | PT0H0M0S |  |  | FIFTH FLOOR | 2027-07-05 | 2027-07-16 | 2027-04-20 | 2027-05-03 | 0 |  |  |  | 431FS |  | SuperAdmin
Column Concreting - Phase I | 42FD505D-25AF-F011-A460-7C70DB2D7E2B | JKR Workshop | 19 | JKR-001 | PT0H0M0S |  |  | FIFTH FLOOR | 2027-08-09 | 2027-08-19 | 2027-05-26 | 2027-06-06 | 0 |  |  |  | 434FS |  | SuperAdmin
Beam Concreting -Phase I | 4AFD505D-25AF-F011-A460-7C70DB2D7E2B | JKR Workshop | 19 | JKR-001 | PT0H0M0S |  |  | ROOF | 2027-08-31 | 2027-09-09 | 2027-06-14 | 2027-06-23 | 0 |  |  |  | 436FS |  | SuperAdmin
Beam Concreting - Phase II | 4CFD505D-25AF-F011-A460-7C70DB2D7E2B | JKR Workshop | 19 | JKR-001 | PT0H0M0S |  |  | ROOF | 2027-09-10 | 2027-09-23 | 2027-06-24 | 2027-07-07 | 0 |  |  |  | 438FS |  | SuperAdmin
Architecture 90% Design | JKR-001-RVW-00001 | JKR Workshop | 19 | JKR-001 | Architecture 90% Design |  | High |  | 2025-10-25 | 2025-10-27 | 2025-10-26 | 2025-10-26 | 49 | [5 empty] | ManojVictor
Architecture | 529D0266-26AF-F011-A460-7C70DB2D7E2B | JKR Workshop ISO | 39 | 0001-JKRM-KR01-0001-A-P01.01 | PT0H0M0S |  |  | Good For Construction | 2026-03-17 | 2028-01-17 | 2026-03-17 | 2028-01-17 | 0 | [5 empty] | SuperAdmin
BASEMENT | DCFC505D-25AF-F011-A460-7C70DB2D7E2B | JKR Workshop ISO | 39 | 0001-JKRM-KR01-0001-A-P01.01 | PT0H0M0S |  |  | SUPERSTRUCTURE | 2028-03-08 | 2028-05-22 | 2028-03-08 | 2028-05-22 | 0 | [5 empty] | SuperAdmin
C101-Site Plan | FA448135-26AF-F011-A460-7C70DB2D7E2B | JKR Workshop ISO | 39 | 0001-JKRM-KR01-0001-A-P01.01 | PT0H0M0S |  |  | Architecture | 2026-07-21 | 2026-08-03 | 2026-07-21 | 2026-08-03 | 0 |  |  |  | 535FS |  | SuperAdmin
A100-Parking Deck Floor Plan | F9448135-26AF-F011-A460-7C70DB2D7E2B | JKR Workshop ISO | 39 | 0001-JKRM-KR01-0001-A-P01.01 | PT0H0M0S |  |  | Architecture | 2026-08-04 | 2026-08-17 | 2026-08-04 | 2026-08-17 | 0 |  |  |  | 536FS |  | SuperAdmin
A101-First Floor Plan | F8448135-26AF-F011-A460-7C70DB2D7E2B | JKR Workshop ISO | 39 | 0001-JKRM-KR01-0001-A-P01.01 | PT0H0M0S |  |  | Architecture | 2026-08-18 | 2026-08-31 | 2026-08-18 | 2026-08-31 | 0 |  |  |  | 537FS |  | SuperAdmin
A102-Second Floor Plan | F7C78B00-26AF-F011-A460-7C70DB2D7E2B | JKR Workshop ISO | 39 | 0001-JKRM-KR01-0001-A-P01.01 | PT0H0M0S |  |  | Architecture | 2026-09-01 | 2026-09-14 | 2026-09-01 | 2026-09-14 | 0 |  |  |  | 538FS |  | SuperAdmin
A103-Third Floor Plan | F6C78B00-26AF-F011-A460-7C70DB2D7E2B | JKR Workshop ISO | 39 | 0001-JKRM-KR01-0001-A-P01.01 | PT0H0M0S |  |  | Architecture | 2026-09-15 | 2026-09-28 | 2026-09-15 | 2026-09-28 | 0 |  |  |  | 539FS |  | SuperAdmin
A104-Fourth Floor Plan | F5C78B00-26AF-F011-A460-7C70DB2D7E2B | JKR Workshop ISO | 39 | 0001-JKRM-KR01-0001-A-P01.01 | PT0H0M0S |  |  | Architecture | 2026-09-29 | 2026-10-12 | 2026-09-29 | 2026-10-12 | 0 |  |  |  | 540FS |  | SuperAdmin
A105-Fifth Floor Plan | 6C28D362-27AF-F011-A460-7C70DB2D7E2B | JKR Workshop ISO | 39 | 0001-JKRM-KR01-0001-A-P01.01 | PT0H0M0S |  |  | Architecture | 2026-10-13 | 2026-10-26 | 2026-10-13 | 2026-10-26 | 0 |  |  |  | 541FS |  | SuperAdmin
A106-Green Roof | 6B28D362-27AF-F011-A460-7C70DB2D7E2B | JKR Workshop ISO | 39 | 0001-JKRM-KR01-0001-A-P01.01 | PT0H0M0S |  |  | Architecture | 2026-10-27 | 2026-11-09 | 2025-12-10 |  | 0 |  |  |  | 542FS |  | SuperAdmin
A107-Roof Plan | 6A28D362-27AF-F011-A460-7C70DB2D7E2B | JKR Workshop ISO | 39 | 0001-JKRM-KR01-0001-A-P01.01 | PT0H0M0S |  |  | Architecture | 2026-11-10 | 2026-11-23 | 2025-11-09 | 2025-11-09 | 0 |  |  |  | 543FS |  | SuperAdmin
A108-First Floor Ceiling Plan | 6928D362-27AF-F011-A460-7C70DB2D7E2B | JKR Workshop ISO | 39 | 0001-JKRM-KR01-0001-A-P01.01 | PT0H0M0S |  |  | Architecture | 2026-11-24 | 2026-12-07 | 2026-11-24 | 2026-12-07 | 0 |  |  |  | 544FS |  | SuperAdmin
A109-Second Floor Ceiling Plan | 6828D362-27AF-F011-A460-7C70DB2D7E2B | JKR Workshop ISO | 39 | 0001-JKRM-KR01-0001-A-P01.01 | PT0H0M0S |  |  | Architecture | 2026-12-08 | 2026-12-21 | 2026-12-08 | 2026-12-21 | 0 |  |  |  | 545FS |  | SuperAdmin
A110-Third Floor Ceiling Plan | 6728D362-27AF-F011-A460-7C70DB2D7E2B | JKR Workshop ISO | 39 | 0001-JKRM-KR01-0001-A-P01.01 | PT0H0M0S |  |  | Architecture | 2026-12-22 | 2027-01-04 | 2026-12-22 | 2027-01-04 | 0 |  |  |  | 546FS |  | SuperAdmin
A111-Fourth Floor Ceiling Plan | 6628D362-27AF-F011-A460-7C70DB2D7E2B | JKR Workshop ISO | 39 | 0001-JKRM-KR01-0001-A-P01.01 | PT0H0M0S |  |  | Architecture | 2027-01-05 | 2027-01-18 | 2027-01-05 | 2027-01-18 | 0 |  |  |  | 547FS |  | SuperAdmin
A112-Fifth Floor Ceiling Plan | 6528D362-27AF-F011-A460-7C70DB2D7E2B | JKR Workshop ISO | 39 | 0001-JKRM-KR01-0001-A-P01.01 | PT0H0M0S |  |  | Architecture | 2027-01-19 | 2027-02-01 | 2027-01-19 | 2027-02-01 | 0 |  |  |  | 548FS |  | SuperAdmin
A200-Existing Conditions Elevations | 6428D362-27AF-F011-A460-7C70DB2D7E2B | JKR Workshop ISO | 39 | 0001-JKRM-KR01-0001-A-P01.01 | PT0H0M0S |  |  | Architecture | 2027-02-02 | 2027-02-15 | 2027-02-02 | 2027-02-15 | 0 |  |  |  | 549FS |  | SuperAdmin
A201-Building Elevations | 6328D362-27AF-F011-A460-7C70DB2D7E2B | JKR Workshop ISO | 39 | 0001-JKRM-KR01-0001-A-P01.01 | PT0H0M0S |  |  | Architecture | 2027-02-16 | 2027-03-01 | 2027-02-16 | 2027-03-01 | 0 |  |  |  | 550FS |  | SuperAdmin
A202-Building Elevations | 6228D362-27AF-F011-A460-7C70DB2D7E2B | JKR Workshop ISO | 39 | 0001-JKRM-KR01-0001-A-P01.01 | PT0H0M0S |  |  | Architecture | 2027-03-02 | 2027-03-15 | 2027-03-02 | 2027-03-15 | 0 |  |  |  | 551FS |  | SuperAdmin
A301-Building Sections | 6128D362-27AF-F011-A460-7C70DB2D7E2B | JKR Workshop ISO | 39 | 0001-JKRM-KR01-0001-A-P01.01 | PT0H0M0S |  |  | Architecture | 2027-03-16 | 2027-03-29 | 2027-03-16 | 2027-03-29 | 0 |  |  |  | 552FS |  | SuperAdmin
A302-Building Sections | 6028D362-27AF-F011-A460-7C70DB2D7E2B | JKR Workshop ISO | 39 | 0001-JKRM-KR01-0001-A-P01.01 | PT0H0M0S |  |  | Architecture | 2027-03-30 | 2027-04-12 | 2027-03-30 | 2027-04-12 | 0 |  |  |  | 553FS |  | SuperAdmin
A303-Building Sections | 5F28D362-27AF-F011-A460-7C70DB2D7E2B | JKR Workshop ISO | 39 | 0001-JKRM-KR01-0001-A-P01.01 | PT0H0M0S |  |  | Architecture | 2027-04-13 | 2027-04-26 | 2027-04-13 | 2027-04-26 | 0 |  |  |  | 554FS |  | SuperAdmin
A304-Building Sections | 5E28D362-27AF-F011-A460-7C70DB2D7E2B | JKR Workshop ISO | 39 | 0001-JKRM-KR01-0001-A-P01.01 | PT0H0M0S |  |  | Architecture | 2027-04-27 | 2027-05-10 | 2027-04-27 | 2027-05-10 | 0 |  |  |  | 555FS |  | SuperAdmin
A305-Building Sections | 5D28D362-27AF-F011-A460-7C70DB2D7E2B | JKR Workshop ISO | 39 | 0001-JKRM-KR01-0001-A-P01.01 | PT0H0M0S |  |  | Architecture | 2027-05-11 | 2027-05-24 | 2027-05-11 | 2027-05-24 | 0 |  |  |  | 556FS |  | SuperAdmin
A306-Building Sections | 5C28D362-27AF-F011-A460-7C70DB2D7E2B | JKR Workshop ISO | 39 | 0001-JKRM-KR01-0001-A-P01.01 | PT0H0M0S |  |  | Architecture | 2027-05-25 | 2027-06-07 | 2027-05-25 | 2027-06-07 | 0 |  |  |  | 557FS |  | SuperAdmin
A307-Building Sections | 5B28D362-27AF-F011-A460-7C70DB2D7E2B | JKR Workshop ISO | 39 | 0001-JKRM-KR01-0001-A-P01.01 | PT0H0M0S |  |  | Architecture | 2027-06-08 | 2027-06-21 | 2027-06-08 | 2027-06-21 | 0 |  |  |  | 558FS |  | SuperAdmin
A401-Typical Public Restroom | 5A28D362-27AF-F011-A460-7C70DB2D7E2B | JKR Workshop ISO | 39 | 0001-JKRM-KR01-0001-A-P01.01 | PT0H0M0S |  |  | Architecture | 2027-06-22 | 2027-07-05 | 2027-06-22 | 2027-07-05 | 0 |  |  |  | 559FS |  | SuperAdmin
A402-Enlarged Live/Work Cores | 2D603370-27AF-F011-A460-7C70DB2D7E2B | JKR Workshop ISO | 39 | 0001-JKRM-KR01-0001-A-P01.01 | PT0H0M0S |  |  | Architecture | 2027-07-06 | 2027-07-19 | 2027-07-06 | 2027-07-19 | 0 |  |  |  | 560FS |  | SuperAdmin
A403-Enlarged Live/Work Cores | 2C603370-27AF-F011-A460-7C70DB2D7E2B | JKR Workshop ISO | 39 | 0001-JKRM-KR01-0001-A-P01.01 | PT0H0M0S |  |  | Architecture | 2027-07-20 | 2027-08-02 | 2027-07-20 | 2027-08-02 | 0 |  |  |  | 561FS |  | SuperAdmin
A404-Residential Lobby | 2B603370-27AF-F011-A460-7C70DB2D7E2B | JKR Workshop ISO | 39 | 0001-JKRM-KR01-0001-A-P01.01 | PT0H0M0S |  |  | Architecture | 2027-08-03 | 2027-08-16 | 2027-08-03 | 2027-08-16 | 0 |  |  |  | 562FS |  | SuperAdmin
A405-Wall Sections | 2A603370-27AF-F011-A460-7C70DB2D7E2B | JKR Workshop ISO | 39 | 0001-JKRM-KR01-0001-A-P01.01 | PT0H0M0S |  |  | Architecture | 2027-08-17 | 2027-08-30 | 2027-08-17 | 2027-08-30 | 0 |  |  |  | 563FS |  | SuperAdmin
A406-Wall Sections | 29603370-27AF-F011-A460-7C70DB2D7E2B | JKR Workshop ISO | 39 | 0001-JKRM-KR01-0001-A-P01.01 | PT0H0M0S |  |  | Architecture | 2027-08-31 | 2027-09-13 | 2027-08-31 | 2027-09-13 | 0 |  |  |  | 564FS |  | SuperAdmin
A501-Details | 811E336A-27AF-F011-A460-7C70DB2D7E2B | JKR Workshop ISO | 39 | 0001-JKRM-KR01-0001-A-P01.01 | PT0H0M0S |  |  | Architecture | 2027-09-14 | 2027-09-27 | 2027-09-14 | 2027-09-27 | 0 |  |  |  | 565FS |  | SuperAdmin
A502-Partition Types | 801E336A-27AF-F011-A460-7C70DB2D7E2B | JKR Workshop ISO | 39 | 0001-JKRM-KR01-0001-A-P01.01 | PT0H0M0S |  |  | Architecture | 2027-09-28 | 2027-10-11 | 2027-09-28 | 2027-10-11 | 0 |  |  |  | 566FS |  | SuperAdmin
A601-Door Schedule | 7F1E336A-27AF-F011-A460-7C70DB2D7E2B | JKR Workshop ISO | 39 | 0001-JKRM-KR01-0001-A-P01.01 | PT0H0M0S |  |  | Architecture | 2027-10-12 | 2027-10-25 | 2027-10-12 | 2027-10-25 | 0 |  |  |  | 567FS |  | SuperAdmin
A602-Schedules | 7E1E336A-27AF-F011-A460-7C70DB2D7E2B | JKR Workshop ISO | 39 | 0001-JKRM-KR01-0001-A-P01.01 | PT0H0M0S |  |  | Architecture | 2027-10-26 | 2027-11-08 | 2027-10-26 | 2027-11-08 | 0 |  |  |  | 568FS |  | SuperAdmin
A901-Perspective From Above | 7D1E336A-27AF-F011-A460-7C70DB2D7E2B | JKR Workshop ISO | 39 | 0001-JKRM-KR01-0001-A-P01.01 | PT0H0M0S |  |  | Architecture | 2027-11-09 | 2027-11-22 | 2027-11-09 | 2027-11-22 | 0 |  |  |  | 569FS |  | SuperAdmin
A902-Stair Towers - Cutaway Views | 7C1E336A-27AF-F011-A460-7C70DB2D7E2B | JKR Workshop ISO | 39 | 0001-JKRM-KR01-0001-A-P01.01 | PT0H0M0S |  |  | Architecture | 2027-11-23 | 2027-12-06 | 2027-11-23 | 2027-12-06 | 0 |  |  |  | 570FS |  | SuperAdmin
A903-3D Views | 7B1E336A-27AF-F011-A460-7C70DB2D7E2B | JKR Workshop ISO | 39 | 0001-JKRM-KR01-0001-A-P01.01 | PT0H0M0S |  |  | Architecture | 2027-12-07 | 2027-12-20 | 2027-12-07 | 2027-12-20 | 0 |  |  |  | 571FS |  | SuperAdmin
A904-Solar Study | 7A1E336A-27AF-F011-A460-7C70DB2D7E2B | JKR Workshop ISO | 39 | 0001-JKRM-KR01-0001-A-P01.01 | PT0H0M0S |  |  | Architecture | 2027-12-21 | 2028-01-03 | 2027-12-21 | 2028-01-03 | 0 |  |  |  | 572FS |  | SuperAdmin
Beam Concreting -Phase I | EAFC505D-25AF-F011-A460-7C70DB2D7E2B | JKR Workshop ISO | 39 | 0001-JKRM-KR01-0001-A-P01.01 | PT0H0M0S |  |  | GROUND FLOOR | 2028-05-23 | 2028-06-02 | 2028-05-23 | 2028-06-02 | 0 |  |  |  | 583FS |  | SuperAdmin
Beam Concreting - Phase II | ECFC505D-25AF-F011-A460-7C70DB2D7E2B | JKR Workshop ISO | 39 | 0001-JKRM-KR01-0001-A-P01.01 | PT0H0M0S |  |  | GROUND FLOOR | 2028-06-05 | 2028-06-16 | 2028-06-05 | 2028-06-16 | 0 |  |  |  | 585FS |  | SuperAdmin
Column Concreting - Phase I | F2FC505D-25AF-F011-A460-7C70DB2D7E2B | JKR Workshop ISO | 39 | 0001-JKRM-KR01-0001-A-P01.01 | PT0H0M0S |  |  | GROUND FLOOR | 2028-07-17 | 2028-07-27 | 2028-07-17 | 2028-07-27 | 0 |  |  |  | 588FS |  | SuperAdmin
Beam Concreting - Phase I | FAFC505D-25AF-F011-A460-7C70DB2D7E2B | JKR Workshop ISO | 39 | 0001-JKRM-KR01-0001-A-P01.01 | PT0H0M0S |  |  | FIRST FLOOR | 2028-08-07 | 2028-08-16 | 2028-08-07 | 2028-08-16 | 0 |  |  |  | 590FS |  | SuperAdmin
Beam Concreting - Phase II | FCFC505D-25AF-F011-A460-7C70DB2D7E2B | JKR Workshop ISO | 39 | 0001-JKRM-KR01-0001-A-P01.01 | PT0H0M0S |  |  | FIRST FLOOR | 2028-08-17 | 2028-08-30 | 2028-08-17 | 2028-08-30 | 0 |  |  |  | 591FS |  | SuperAdmin
Column Concreting - Phase I | 02FD505D-25AF-F011-A460-7C70DB2D7E2B | JKR Workshop ISO | 39 | 0001-JKRM-KR01-0001-A-P01.01 | PT0H0M0S |  |  | FIRST FLOOR | 2028-09-28 | 2028-10-10 | 2028-09-28 | 2028-10-10 | 0 |  |  |  | 595FS |  | SuperAdmin
Beam Concreting -Phase I | 0AFD505D-25AF-F011-A460-7C70DB2D7E2B | JKR Workshop ISO | 39 | 0001-JKRM-KR01-0001-A-P01.01 | PT0H0M0S |  |  | SECOND FLOOR | 2028-11-02 | 2028-11-14 | 2028-11-02 | 2028-11-14 | 0 |  |  |  | 598FS |  | SuperAdmin
Beam Concreting - Phase II | 0CFD505D-25AF-F011-A460-7C70DB2D7E2B | JKR Workshop ISO | 39 | 0001-JKRM-KR01-0001-A-P01.01 | PT0H0M0S |  |  | SECOND FLOOR | 2028-11-15 | 2028-11-28 | 2028-11-15 | 2028-11-28 | 0 |  |  |  | 599FS |  | SuperAdmin
Column Concreting - Phase I | 12FD505D-25AF-F011-A460-7C70DB2D7E2B | JKR Workshop ISO | 39 | 0001-JKRM-KR01-0001-A-P01.01 | PT0H0M0S |  |  | SECOND FLOOR | 2028-12-20 | 2029-01-01 | 2028-12-20 | 2029-01-01 | 0 |  |  |  | 602FS |  | SuperAdmin
Beam Concreting -Phase I | 1AFD505D-25AF-F011-A460-7C70DB2D7E2B | JKR Workshop ISO | 39 | 0001-JKRM-KR01-0001-A-P01.01 | PT0H0M0S |  |  | THIRD FLOOR | 2029-01-11 | 2029-01-22 | 2029-01-11 | 2029-01-22 | 0 |  |  |  | 604FS |  | SuperAdmin
Beam Concreting - Phase II | 1CFD505D-25AF-F011-A460-7C70DB2D7E2B | JKR Workshop ISO | 39 | 0001-JKRM-KR01-0001-A-P01.01 | PT0H0M0S |  |  | THIRD FLOOR | 2029-01-23 | 2029-02-05 | 2029-01-23 | 2029-02-05 | 0 |  |  |  | 606FS |  | SuperAdmin
Column Concreting - Phase I | 22FD505D-25AF-F011-A460-7C70DB2D7E2B | JKR Workshop ISO | 39 | 0001-JKRM-KR01-0001-A-P01.01 | PT0H0M0S |  |  | THIRD FLOOR | 2029-02-27 | 2029-03-09 | 2029-02-27 | 2029-03-09 | 0 |  |  |  | 609FS |  | SuperAdmin
Beam Concreting -Phase I | 2AFD505D-25AF-F011-A460-7C70DB2D7E2B | JKR Workshop ISO | 39 | 0001-JKRM-KR01-0001-A-P01.01 | PT0H0M0S |  |  | FOURTH FLOOR | 2029-03-21 | 2029-03-30 | 2029-03-21 | 2029-03-30 | 0 |  |  |  | 611FS |  | SuperAdmin
Beam Concreting - Phase II | 2CFD505D-25AF-F011-A460-7C70DB2D7E2B | JKR Workshop ISO | 39 | 0001-JKRM-KR01-0001-A-P01.01 | PT0H0M0S |  |  | FOURTH FLOOR | 2029-04-02 | 2029-04-13 | 2029-04-02 | 2029-04-13 | 0 |  |  |  | 613FS |  | SuperAdmin
Column Concreting - Phase I | 32FD505D-25AF-F011-A460-7C70DB2D7E2B | JKR Workshop ISO | 39 | 0001-JKRM-KR01-0001-A-P01.01 | PT0H0M0S |  |  | FOURTH FLOOR | 2029-05-07 | 2029-05-17 | 2029-05-07 | 2029-05-17 | 0 |  |  |  | 616FS |  | SuperAdmin
Beam Concreting -Phase I | 3AFD505D-25AF-F011-A460-7C70DB2D7E2B | JKR Workshop ISO | 39 | 0001-JKRM-KR01-0001-A-P01.01 | PT0H0M0S |  |  | FIFTH FLOOR | 2029-05-29 | 2029-06-07 | 2029-05-29 | 2029-06-07 | 0 |  |  |  | 618FS |  | SuperAdmin
Beam Concreting - Phase II | 3CFD505D-25AF-F011-A460-7C70DB2D7E2B | JKR Workshop ISO | 39 | 0001-JKRM-KR01-0001-A-P01.01 | PT0H0M0S |  |  | FIFTH FLOOR | 2029-06-08 | 2029-06-21 | 2029-06-08 | 2029-06-21 | 0 |  |  |  | 620FS |  | SuperAdmin
Column Concreting - Phase I | 42FD505D-25AF-F011-A460-7C70DB2D7E2B | JKR Workshop ISO | 39 | 0001-JKRM-KR01-0001-A-P01.01 | PT0H0M0S |  |  | FIFTH FLOOR | 2029-07-13 | 2029-07-25 | 2029-07-13 | 2029-07-25 | 0 |  |  |  | 623FS |  | SuperAdmin
Beam Concreting -Phase I | 4AFD505D-25AF-F011-A460-7C70DB2D7E2B | JKR Workshop ISO | 39 | 0001-JKRM-KR01-0001-A-P01.01 | PT0H0M0S |  |  | ROOF | 2029-08-06 | 2029-08-15 | 2029-08-06 | 2029-08-15 | 0 |  |  |  | 625FS |  | SuperAdmin
Beam Concreting - Phase II | 4CFD505D-25AF-F011-A460-7C70DB2D7E2B | JKR Workshop ISO | 39 | 0001-JKRM-KR01-0001-A-P01.01 | PT0H0M0S |  |  | ROOF | 2029-08-16 | 2029-08-29 | 2029-08-16 | 2029-08-29 | 0 |  |  |  | 627FS |  | SuperAdmin
Materials used | 0001-XXXX-XX01-RVW-0001-A-P01.01 | JKR Workshop ISO | 39 | 0001-JKRM-KR01-0001-A-P01.01 | What is materials used in construction? |  | High |  | 2025-10-28 | 2025-10-31 | 2025-10-27 | 2025-10-30 | 45 | [5 empty] | SuperAdmin
18001-DB01C-2-263-409-BOM_R01-FOUNDATION FOR AC PLANT 3 & 4.xlsx | 2911-RVW-00001 | L&T Shipbuilding | 62 | 2911 | 18001-DB01C-2-263-409-BOM_R01-FOUNDATION FOR AC PLANT 3 & 4.xlsx | 3s-Rw-WF | High | Spool Drawing of Fire Main System | 2025-12-01 | 2025-12-10 | 2025-11-30 | 2025-12-09 | 17 | Open | Open | 229 |  |  | ManojVictor
18001-DB01C-2-263-409-R01-FOUNDATION FOR AC PLANT 3 & 4.dwg | 2911-RVW-00002 | L&T Shipbuilding | 62 | 2911 | 18001-DB01C-2-263-409-R01-FOUNDATION FOR AC PLANT 3 & 4.dwg | 3s-Rw-WF | High | Spool Drawing of Fire Main System | 2025-12-04 | 2025-12-09 | 2025-12-03 | 2025-12-08 | 18 | Open | Open | 229 |  |  | ManojVictor
18001-DB01C-2-263-409-R01-FDN FOR AC PLANT 3&4.csv | 2911-RVW-00003 | L&T Shipbuilding | 62 | 2911 | 18001-DB01C-2-263-409-R01-FDN FOR AC PLANT 3&4.csv | 3s-Rw-WF | High | Spool Drawing of Fire Main System | 2025-12-11 | 2025-12-18 | 2025-12-10 | 2025-12-17 | 11 | Open | Open | 229 |  |  | ManojVictor
Approval of documents 2 | JKR-001-RVW-123456 | JKR Workshop | 19 | JKR-001 | Documents related to foundation | 1s-Rw-WF | High |  | 2025-12-12 | 2025-12-19 | 2025-12-11 | 2025-12-18 | 10 | Open | Open | 30 |  |  | KirubakaranCandassamy