## Sheet1
Name | Code | Description | Location | Project Id | Workflow Status | Review Status | Review Id | Type | Root Cause | Placement | Start Date | Target Date | Lagged Days | Version
floor fixing | T23101-ISS-0dsd1 | The floor fixing issue in the bedroom requires immediate attention due to non-uniform thickness. This flooring concern, currently without an estimated cost, necessitates a comprehensive assessment. Addressing this critical construction site design issue effectively is paramount for resolution. |  | 17 | Open | Open | 19 | Flooring | Thickness is not uniform | Bed room | 2025-10-31 | 2025-10-31 | 45
ISSUE01 | 1101-XXXX-XX01-ISS-0001-A-P01.01 | ISSUE01, located in Chennai, involves a painting issue on the first-floor ceiling of room 1. The root cause has been identified as oversized duct dimensions. Remediation for this specific painting problem is estimated at 1000. | chennai | 21 | Rejected | Rejected | 46 | Painting | Duct dimensions are high | Ceiling reference with room 1 in first floor | 2025-10-23 | 2025-10-30 | -
ISS002 | 2521-XXXX-XX01-ISS-0001-A-P01.01 | Issue ISS002 pertains to a kitchen design flaw located on the wall of the master bedroom in Chennai. The primary root cause identified is a lack of a painter, leading to an estimated rectification cost of 1000. This issue requires immediate attention to maintain project quality. | chennai | 21 | Approved | Approved | 46 | Kitchen design | Lack of painter | Wall of master bed room | 2025-10-23 | 2025-10-30 | -
iss1 | bspv123-ISS-nr584 | Issue iss1 requires attention due to an unspecified type and placement. The problem's location and root cause are currently undetermined, preventing an accurate estimated cost. A comprehensive description is needed to assess the impact and formulate a resolution plan for this critical construction site/design issue. |  | 20 | Approved | Approved | 39 | Kitchen design | Not fixed in center of wall | Position in right side of wall in 2nd floor bedroom 1 | 2025-10-23 | 2025-10-31 | -
iss24 | bspv123-ISS-gr432154 | test |  | 20 | Open | Open | 39 | Clour of painting | Painter | Main entrance of house | 2025-10-23 | 2025-11-09 | 40
Iss-458 | 1791-XXXX-XX01-ISS-0001-A-P01.01 | Issue Iss-458 involves a water pipe problem located in the wall of the master bedroom in Chennai. The root cause has been identified as a lack of a painter, leading to an estimated repair cost of 5000. This issue requires immediate attention to prevent further damage. | chennai | 21 | Open | Open | 46 | Water pipe | Lack of painter | Wall of master bed room | 2025-10-23 | 2025-10-30 | 46
uMiFbsHaiK | TestFF1-ISS-0a1972 | KNJCmTOD | KNJCmTOD | 24 | Approved | Approved | 55 | HAVC of second floor | Duct dimensions are high | Ceiling reference with room 1 in first floor | 2025-10-24 | 2025-10-29 | -
Door installation not as per plan | JKR-001-ISS-00007 | Door placement is not as per plan | L2 | 19 | Open | Open | 23 | 36" x 84" (60 MIN) | Location | Door-Passage-Single-Flush [1206137] | 2025-10-24 | 2025-10-24 | 50
Toilet pipe is not installed | JKR-001-ISS-00006 | Toilet fixture is missing | L1 - Block 37 | 19 | Open | Open | 23 | 19" Seat Height | Location | Toilet-Commercial-Wall-3D [1921146] | 2025-10-24 | 2025-10-24 | 50
Interior of washroom 1 | JKR-001-ISS-00005 | Mirror not installed in model | L1 - Block 37 | 19 | Rejected | Rejected | 17 | 28" x 48" | Location | Mirror [1390239] | 2025-10-24 | 2025-10-24 | -
Duct cover net or mesh is not installed | JKR-001-ISS-00004 | Duct opening cover missing | R3 | 19 | Open | Open | 23 | Insulation on Metal Deck - EPDM | Location | Basic Roof [882818] | 2025-10-24 | 2025-10-24 | 50
Rail Placement is incorrect | JKR-001-ISS-00003 | Placement issue | undefined | 19 | Open | Open | 17 | Road Striping | Location | Top Rail Type [2153936] | 2025-10-24 | 2025-10-24 | 50
Partition wall issue | JKR-001-ISS-00002 | Partition wall is missing | L4 | 19 | Approved | Approved | 17 | Interior - 7 1/4" Partition (NR) | Location | Basic Wall [1280889] | 2025-10-24 | 2025-10-24 | -
Placement of Block not as per plan | JKR-001-ISS-00001 | Change Block 31 placement required | Project | 19 | Open | Open | 23 | Block 31 | Location | Block 31 [1139274] | 2025-10-24 | 2025-10-24 | 50
Pergola Beam Grade of Steel not right | JKR-001-ISS-00008 | Pergola Beam Grade of Steel not right | L1 | 19 | Open | Open | 17 | Pergola Beam Grade of Steel not right | Location | Pergola Beam Grade of Steel not right | 2025-10-24 | 2025-10-27 | 49
Basic Wall [120317] | TestFF1-ISS-01ais | Name: Basic Wall [120317], PlacementId: Basic Wall [120317], TypeId: 6", Location: Floor 30, EstimatedCost: 0 | Floor 30 | 24 | Open | Open | 55 | 6" | Location | Basic Wall [120317] | 2025-10-25 | 2025-10-25 | 50
Basic Wall [163089] | JKR-AA-ISS-00457 | Name: Basic Wall [163089], PlacementId: Basic Wall [163089], TypeId: 6", Location: Floor 30, EstimatedCost: 0 | Floor 30 | 27 | Open | Open | 75 | 6" | Location | Basic Wall [163089] | 2025-10-25 | 2025-10-25 | 50
Basic Wall [163089] (1) | ee9330da-b935-4024-8efa-3fa23ba77fbc | Name: Basic Wall [163089], PlacementId: Basic Wall [163089], TypeId: 6", Location: Floor 30, EstimatedCost: 0 | L1 | 27 | Open | Open | 75 | Basic Wall [163089] | Location | Basic Wall [163089] | 2025-10-25 | 2025-10-25 | 50
Basic Wall [120317] | 40a0b58b-61ff-4ec3-a0fc-21aae7bea20a | Name: Basic Wall [120317], PlacementId: Basic Wall [120317], TypeId: 6", Location: Floor 30, EstimatedCost: 0 | L1 | 21 | Open | Open | 62 | Basic Wall [120317] | Location | Basic Wall [120317] | 2025-10-25 | 2025-10-25 | 50
Iso1a | 805d8d77-4258-4985-8bc4-aa602bdbb330 | TEst issue for import | L1 | 24 | Open | Open | 55 | Iso1a | Location | Iso1a | 2025-10-25 | 2025-10-25 | 50
Quality - Paint work | JKR-001-ISS-00009 | Quality - Paint work - Tower 1, floor 4, flat 1, Room 2, second coat paint not applied |  | 19 | Open | Open | 23 | Painting | Painter | Wall of master bed room | 2025-10-25 | 2025-10-28 | 48
Safety - PPE | JKR-001-ISS-00010 | Labours working without PPE on site |  | 19 | Approved | Approved | 17 | Water pipe | Leakage | Exterior walls | 2025-10-25 | 2025-10-28 | -
Floor [665246] | TestFF1-ISS-32123 | Name: Floor [665246], PlacementId: Floor [665246], TypeId: NW Concrete on Metal Deck, Location: L3, EstimatedCost: 0 | L3 | 24 | Open | Open | 55 | NW Concrete on Metal Deck | Location | Floor [665246] | 2025-10-25 | 2025-10-25 | 50
Basic Wall [601472] | 5643 | Name: Basic Wall [601472], PlacementId: Basic Wall [601472], TypeId: Concrete 24", Location: Top of Footing, EstimatedCost: 0 | Top of Footing | 1 | Open | Open | 78 | Concrete 24" | Location | Basic Wall [601472] | 2025-10-25 | 2025-10-25 | 50
Basic Wall [935922] | 6568 | Name: Basic Wall [935922], PlacementId: Basic Wall [935922], TypeId: Concrete 18", Location: L1_43_High, EstimatedCost: 0 | L1_43_High | 1 | Open | Open | 1 | Concrete 18" | Location | Basic Wall [935922] | 2025-10-25 | 2025-10-25 | 50
Basic Wall [2060639] | JKR-001-ISS-EIR-01 | Name: Basic Wall [2060639], PlacementId: Basic Wall [2060639], TypeId: Generic - 4", Location: R2, EstimatedCost: 0 | R2 | 19 | Approved | Approved | 17 | Generic - 4" | Location | Basic Wall [2060639] | 2025-10-25 | 2025-10-25 | -
Basic Wall [601278] | 4323 | Name: Basic Wall [601278], PlacementId: Basic Wall [601278], TypeId: Concrete 24", Location: Top of Footing, EstimatedCost: 0 | Top of Footing | 1 | Open | Open | 78 | Concrete 24" | Location | Basic Wall [601278] | 2025-10-25 | 2025-10-25 | 50
Basic Wall [139854] | TestFF1-ISS-hgity | Name: Basic Wall [139854], PlacementId: Basic Wall [139854], TypeId: Exterior - Insulation on Masonry, Location: 01 - Entry Level, EstimatedCost: 0 | 01 - Entry Level | 24 | Open | Open | 55 | Exterior - Insulation on Masonry | Location | Basic Wall [139854] | 2025-10-25 | 2025-10-25 | 50
Basic Wall [139854] | TestFF1-ISS-hgity | Name: Basic Wall [139854], PlacementId: Basic Wall [139854], TypeId: Exterior - Insulation on Masonry, Location: 01 - Entry Level, EstimatedCost: 0 | 01 - Entry Level | 24 | Open | Open | 55 | Exterior - Insulation on Masonry | Location | Basic Wall [139854] | 2025-10-25 | 2025-10-25 | 50
Stair [140885] | TestFF1-ISS-0asfe | Name: Stair [140885], PlacementId: Stair [140885], TypeId: 190mm max riser 250mm going, Location: Floor 30, EstimatedCost: 0 | Floor 30 | 24 | Open | Open | 55 | 190mm max riser 250mm going | Location | Stair [140885] | 2025-10-25 | 2025-10-25 | 50
K-Series Bar Joist-Angle Web [720205] | 0001-XXXX-XX01-ISS-0001-A-P01.82 | Name: K-Series Bar Joist-Angle Web [720205], PlacementId: K-Series Bar Joist-Angle Web [720205], TypeId: 16K2, Location: R2 TOS, EstimatedCost: 0 | R2 TOS | 1 | Open | Open | 78 | 16K2 | Location | K-Series Bar Joist-Angle Web [720205] | 2025-10-26 | 2025-10-26 | 50
Round Duct [1485080] | 0001-XXXX-XX01-ISS-0001-A-P01.71 | Name: Round Duct [1485080], PlacementId: Round Duct [1485080], TypeId: Tees, Location: L1 - Block 37, EstimatedCost: 0 | L1 - Block 37 | 1 | Open | Open | 78 | Tees | Location | Round Duct [1485080] | 2025-10-26 | 2025-10-26 | 50
K-Series Bar Joist-Angle Web [792267] | JKR001-ISS-01234 | Name: K-Series Bar Joist-Angle Web [792267], PlacementId: K-Series Bar Joist-Angle Web [792267], TypeId: 16K6, Location: L4 TOS, EstimatedCost: 0 | L4 TOS | 4 | Open | Open | 109 | 16K6 | Location | K-Series Bar Joist-Angle Web [792267] | 2025-10-26 | 2025-10-26 | 50
WuyZJIpwKn | TestFF1-ISS-0a9623 | XeXoSXul | XeXoSXul | 24 | Approved | Approved | 55 | HAVC of second floor | Duct dimensions are high | Ceiling reference with room 1 in first floor | 2025-10-26 | 2025-10-31 | -
WJCTNJsAyZ | TestFF1-ISS-0a6210 | suucBcrK | suucBcrK | 24 | Open | Open | 55 | HAVC of second floor | Duct dimensions are high | Ceiling reference with room 1 in first floor | 2025-10-26 | 2025-10-31 | 45
saxYggkWdV | TestFF1-ISS-0a7239 | cSOQnnDp | cSOQnnDp | 24 | Approved | Approved | 55 | HAVC of second floor | Duct dimensions are high | Ceiling reference with room 1 in first floor | 2025-10-26 | 2025-10-31 | -
Basic Wall [593197] | 145 | Name: Basic Wall [593197], PlacementId: Basic Wall [593197], TypeId: Generic - 12", Location: L1 - Block 43, EstimatedCost: 0 | L1 - Block 43 | 21 | Open | Open | 62 | Generic - 12" | Location | Basic Wall [593197] | 2025-10-26 | 2025-10-26 | 50
78Basic Wall [593198] | 14547 | Name: 78Basic Wall [593198], PlacementId: Basic Wall [593198], TypeId: Generic - 12", Location: L1 - Block 43, EstimatedCost: 0 | L1 - Block 43 | 21 | Open | Open | 62 | Generic - 12" | Location | Basic Wall [593198] | 2025-10-26 | 2025-10-26 | 50
Basic Wall [608751] | TestFF1-ISS-00432 | Name: Basic Wall [608751], PlacementId: Basic Wall [608751], TypeId: Block 43 w Brick Banding, Location: L3, EstimatedCost: 0 | L3 | 24 | Open | Open | 55 | Block 43 w Brick Banding | Location | Basic Wall [608751] | 2025-10-26 | 2025-10-26 | 50
Basic Wall [6087f51] | TestFF1-ISS-34reef | Name: Basic Wall [6087f51], PlacementId: Basic Wall [608751], TypeId: Block 43 w Brick Banding, Location: L3, EstimatedCost: 0 | L3 | 24 | Open | Open | 55 | Block 43 w Brick Banding | Location | Basic Wall [608751] | 2025-10-26 | 2025-10-26 | 50
Block 43 Pilasters [609299] | TestFF1-ISS-00ffg | Name: Block 43 Pilasters [609299], PlacementId: Block 43 Pilasters [609299], TypeId: 15" x 30", Location: L1 - Block 43, EstimatedCost: 0 | L1 - Block 43 | 24 | Open | Open | 55 | 15" x 30" | Location | Block 43 Pilasters [609299] | 2025-10-26 | 2025-10-26 | 50
Brownsville 141 [1160010] | TestFF1-ISS-00fdd | Name: Brownsville 141 [1160010], PlacementId: Brownsville 141 [1160010], TypeId: Brownsville 141, Location: Project, EstimatedCost: 0 | Project | 24 | Open | Open | 55 | Brownsville 141 | Location | Brownsville 141 [1160010] | 2025-10-26 | 2025-10-26 | 50
Floor [935216] | TestFF1-ISS-00cvx | Name: Floor [935216], PlacementId: Floor [935216], TypeId: Concrete 12", Location: L1_43_High, EstimatedCost: 0 | L1_43_High | 24 | Open | Open | 55 | Concrete 12" | Location | Floor [935216] | 2025-10-26 | 2025-10-26 | 50
Basic Wall [1235583] | TestFF1-ISS-0dsfa | Name: Basic Wall [1235583], PlacementId: Basic Wall [1235583], TypeId: Party - 6 1/8" (2-hr), Location: L2, EstimatedCost: 0 | L2 | 24 | Open | Open | 55 | Party - 6 1/8" (2-hr) | Location | Basic Wall [1235583] | 2025-10-26 | 2025-10-26 | 50
W Shapes [626834] | TestFF1-ISS-e2324 | Name: W Shapes [626834], PlacementId: W Shapes [626834], TypeId: W18x55, Location: L3 TOS, EstimatedCost: 0 | L3 TOS | 24 | Open | Open | 55 | W18x55 | Location | W Shapes [626834] | 2025-10-26 | 2025-10-26 | 50
Lighting and Appliance Panelboard - 208V MCB [1415147] | TestFF1-ISS-0tred | Name: Lighting and Appliance Panelboard - 208V MCB [1415147], PlacementId: Lighting and Appliance Panelboard - 208V MCB [1415147], TypeId: 100 A, Location: , EstimatedCost: 0 | undefined | 24 | Open | Open | 55 | 100 A | Location | Lighting and Appliance Panelboard - 208V MCB [1415147] | 2025-10-26 | 2025-10-26 | 50
Floor [1139554] | TestFF1-ISS-dfd43 | Name: Floor [1139554], PlacementId: Floor [1139554], TypeId: Sidewalk, Location: Project, EstimatedCost: 0 | Project | 24 | Open | Open | 55 | Sidewalk | Location | Floor [1139554] | 2025-10-26 | 2025-10-26 | 50
369Duplex Receptacle [1419782] | 369 | Name: 369Duplex Receptacle [1419782], PlacementId: Duplex Receptacle [1419782], TypeId: GFCI, Location: , EstimatedCost: 0 | undefined | 21 | Open | Open | 46 | GFCI | Location | Duplex Receptacle [1419782] | 2025-10-26 | 2025-10-26 | 50
PV Inverter [1436615] | vg567 | Name: PV Inverter [1436615], PlacementId: PV Inverter [1436615], TypeId: 36"x26.5", Location: R2, EstimatedCost: 0 | R2 | 21 | Open | Open | 1 | 36"x26.5" | Location | PV Inverter [1436615] | 2025-10-27 | 2025-10-27 | 49
Duplex Receptacle [1408891] | fsdf2345 | Name: Duplex Receptacle [1408891], PlacementId: Duplex Receptacle [1408891], TypeId: GFCI, Location: , EstimatedCost: 0 | undefined | 21 | Open | Open | 1 | GFCI | Location | Duplex Receptacle [1408891] | 2025-10-27 | 2025-10-27 | 49
Basic Wall [596479]145 | 1289 | Name: Basic Wall [596479]145, PlacementId: Basic Wall [596479], TypeId: Concrete 12", Location: L1_43_High, EstimatedCost: 0 | L1_43_High | 21 | Open | Open | 62 | Concrete 12" | Location | Basic Wall [596479] | 2025-10-27 | 2025-10-27 | 49
sLohYwMKRx | TestFF1-ISS-0a1828 | HPrASDjZ | HPrASDjZ | 24 | Approved | Approved | 55 | HAVC of second floor | Duct dimensions are high | Ceiling reference with room 1 in first floor | 2025-10-27 | 2025-11-01 | -
Wall Sweep [1969691] | JKR-001-ISS-1969691 | Dont approve payment, reason: incomplete: Name: Wall Sweep [1969691], PlacementId: Wall Sweep [1969691], TypeId: Coping_Core Wall - Concrete & Rainscreen, Location: Parapet 2, EstimatedCost: 0 | Parapet 2 | 19 | Open | Open | 17 | Coping_Core Wall - Concrete & Rainscreen | Location | Wall Sweep [1969691] | 2025-10-27 | 2025-10-27 | 49
Round Duct [1466529] | JKR-001-ISS-CLASH-01 | Name: Round Duct [1466529], PlacementId: Round Duct [1466529], TypeId: Tees, Location: L4, EstimatedCost: 0 | L4 | 19 | Open | Open | 23 | Tees | Location | Round Duct [1466529] | 2025-10-27 | 2025-10-27 | 49
D589uplex Receptacle [1420854] | W589 | Name: D589uplex Receptacle [1420854], PlacementId: Duplex Receptacle [1420854], TypeId: GFCI, Location: , EstimatedCost: 0 | undefined | 21 | Open | Open | 62 | GFCI | Location | Duplex Receptacle [1420854] | 2025-10-27 | 2025-10-27 | 49
wGNFvMBDXF | TestFF1-ISS-00212 | oLGiilwR |  | 24 | Open | Open | 55 | HAVC of second floor | Duct dimensions are high | Ceiling reference with room 1 in first floor | 2025-11-01 | 2025-11-02 | 45
DMzichBWUe03 | TestFF1-ISS-0i863 | LoChmGQTszyYxkLl |  | 24 | Open | Open | 55 | HAVC of second floor | Duct dimensions are high | Ceiling reference with room 1 in first floor | 2025-10-28 | 2025-11-02 | 45
cvLVKTfRmK | TestFF1-ISS-00957 | WeywItNa |  | 24 | Open | Open | 55 | HAVC of second floor | Duct dimensions are high | Ceiling reference with room 1 in first floor | 2025-11-01 | 2025-11-02 | 45
DijuYysDHH | TestFF1-ISS-0a1224 | KEFyoUMZ | KEFyoUMZ | 24 | Approved | Approved | 55 | HAVC of second floor | Duct dimensions are high | Ceiling reference with room 1 in first floor | 2025-10-28 | 2025-11-02 | -
TS_Rectangular and Square Hollow Tubes-Column [43551222] | JKR-001-ISS-00435 | An issue has been identified with the TS_Rectangular and Square Hollow Tubes-Column (43551222), specifically type TS_75x75x5, situated on the 4TH STOREY. The unacceptable quality of this placement, attributed to its location, necessitates immediate attention. The estimated cost for rectification is 45. Payment for this element should be placed on hold. | 4TH STOREY | 19 | Open | Open | 17 | TS_75x75x5 | Location | TS_Rectangular and Square Hollow Tubes-Column [43551222] | 2025-10-28 | 2025-10-28 | 48
W Shapes [627740] | JKR-001-ISS-06277 | Name: W Shapes [627740], PlacementId: W Shapes [627740], TypeId: W18x55, Location: L3 TOS, EstimatedCost: 0 | L3 TOS | 19 | Approved | Approved | 17 | W18x55 | Location | W Shapes [627740] | 2025-10-28 | 2025-10-28 | -
rehiSUIFHT | TestFF1-ISS-00497 | DeteSrEl |  | 24 | Open | Open | 55 | HAVC of second floor | Duct dimensions are high | Ceiling reference with room 1 in first floor | 2025-11-01 | 2025-11-02 | 45
Corinthian Column Schematic (with Pedestal) [1161167] | JKR-001-ISS-1161165 | This issue pertains to the "Corinthian Column Schematic (with Pedestal) [1161167]" of type "Flex," located at L1 - Block 37. The root cause is identified as "Location." Do not approve this item; stop payment. The estimated cost for this specific placement is 0. | L1 - Block 37 | 19 | Open | Open | 17 | Flex | Location | Corinthian Column Schematic (with Pedestal) [1161167] | 2025-10-29 | 2025-10-29 | 47
Round Duct [1537733] | JKR-001-ISS-00012 | Name: Round Duct [1537733], PlacementId: Round Duct [1537733], TypeId: Tees, Location: L2, EstimatedCost: 0 | L2 | 19 | Open | Open | 110 | Tees | Location | Round Duct [1537733] | 2025-10-29 | 2025-10-29 | 47
Floor [2134315] | JKR-001-ISS-2134315a | Damaged panel noted; do not approve payment; Name: Floor [2134315], PlacementId: Floor [2134315], TypeId: Concrete Slab 6", Location: Parking, EstimatedCost: 45 | Parking | 19 | Approved | Approved | 17 | Concrete Slab 6" | Location | Floor [2134315] | 2025-10-31 | 2025-10-31 | -
Column Mismatching issue | JKR-001-ISS-00Z01 | A significant Column Mismatching issue has been identified in Tower C, specifically affecting the HAVC system of the second floor. The problem is located in Bedroom 1, positioned on the right side of the wall. The root cause has been determined as an excessively large opening in the wall, with an estimated rectification cost of 140000. | Tower C | 19 | Open | Open | 23 | HAVC of second floor | Opening in wall is large | Position in right side of wall in 2nd floor bedroom 1 | 2025-11-01 | 2025-12-01 | 24
Reinforcement bars incorrect storage | JKR-001-ISS-00022 | Reinforcement bars are being stored incorrectly, which may cause damage or quality issues. This needs to be resolved immediately. |  | 19 | Open | Open | 17 | Concrete Slab 6" | Quantity is not proper | Ground floor | 2025-11-03 | 2025-11-08 | 40
Slab Grade check | bcb45913-2588-4dba-9cc1-a06e05291d76 | Slab Grade check | L1 | 19 | Open | Open | 23 | Slab Grade check | Location | Slab Grade check | 2025-11-04 | 2025-11-04 | 43
Structural defect in panel | JKR-001-ISS-VTT001 | Detected structural defect in concrete panel due to improper curing. Requires immediate inspection and repair before proceeding with next phase. |  | 19 | Open | Open | 110 | Painting | Lack of painter | Ceiling reference with room 1 in first floor | 2025-11-05 | 2025-11-08 | 40
Structure Framing | JKR-001-ISS-STR004 | structure framing plan is not issued on the site till now what's the status of the framing plan. |  | 19 | Open | Open | 17 | Painting | Lack of painter | Wall of master bed room | 2025-11-05 | 2025-11-09 | 40
Basic Wall [1454223] | JKR-001-ISS-12345 | Name: Basic Wall [1454223], PlacementId: Basic Wall [1454223], TypeId: Chase - GWB & Metal Stud 6 5/8", Location: L3, EstimatedCost: 0 | L3 | 19 | Open | Open | 17 | Chase - GWB & Metal Stud 6 5/8" | Location | Basic Wall [1454223] | 2025-11-06 | 2025-11-06 | 41
Wall Arc | JKR-001-ISS-0W004 | Name: Wall Arc, PlacementId: Wall Sweep [1969691], TypeId: Coping_Core Wall - Concrete & Rainscreen, Location: Parapet 2, EstimatedCost: 0 | Parapet 2 | 19 | Open | Open | 17 | Coping_Core Wall - Concrete & Rainscreen | Location | Wall Sweep [1969691] | 2025-11-06 | 2025-11-06 | 41
Opening | JKR-001-ISS-WA004 | Name: Opening, PlacementId: Basic Wall [1323507], TypeId: Exterior - 10 1/4" Rainscreen w Insultation on Metal Stud, Location: R2, EstimatedCost: 0 | R2 | 19 | Open | Open | 17 | Exterior - 10 1/4" Rainscreen w Insultation on Metal Stud | Location | Basic Wall [1323507] | 2025-11-06 | 2025-11-06 | 41
Conduit with Fittings [1537147] | JKR-001-ISS-00695 | Name: Conduit with Fittings [1537147], PlacementId: Conduit with Fittings [1537147], TypeId: Electrical Metallic Tubing (EMT), Location: L2, EstimatedCost: 0 | L2 | 19 | Open | Open | 17 | Electrical Metallic Tubing (EMT) | Location | Conduit with Fittings [1537147] | 2025-11-06 | 2025-11-06 | 41
Fire Suppression Control Panel [3881888] | JKR-001-ISS-388188 | Name: Fire Suppression Control Panel [3881888], PlacementId: Fire Suppression Control Panel [3881888], TypeId: Fire Suppression Control Panel, Location: Level 1, EstimatedCost: 0 | Level 1 | 19 | Approved | Approved | 17 | Fire Suppression Control Panel | Location | Fire Suppression Control Panel [3881888] | 2025-11-10 | 2025-11-10 | -
Railing [862857] | JKR-001-ISS-123498MV | Name: Railing [862857], PlacementId: Railing [862857], TypeId: jkrAR_rlg_TPm_(TPm001a)-3 Site - Chainlink Fence, Location: Aras Tanah, EstimatedCost: 0 | Aras Tanah | 19 | Open | Open | 17 | jkrAR_rlg_TPm_(TPm001a)-3 Site - Chainlink Fence | Location | Railing [862857] | 2025-11-13 | 2025-11-13 | 36
Floor [2134315] (1) | JKR-001-ISS-00025 | Damaged panel noted; do not approve payment; Name: Floor [2134315], PlacementId: Floor [2134315], TypeId: Concrete Slab 6", Location: Parking, EstimatedCost: 45 | L1 | 19 | Open | Open | 23 | Floor [2134315] | Location | Floor [2134315] | 2025-10-31 | 2025-10-31 | 45
Partition wall issue (1) | 47fcac3c-9d5a-44cc-ab32-7a2db8b6b450 | Partition wall is missing | L1 | 19 | Open | Open | 23 | Partition wall issue | Location | Partition wall issue | 2025-10-24 | 2025-10-24 | 50
Basic Wall [1454223] (1) | ddb3d3ac-1724-43bc-9113-900fc36f8651 | Name: Basic Wall [1454223], PlacementId: Basic Wall [1454223], TypeId: Chase - GWB & Metal Stud 6 5/8", Location: L3, EstimatedCost: 0 | L1 | 19 | Open | Open | 23 | Basic Wall [1454223] | Location | Basic Wall [1454223] | 2025-11-06 | 2025-11-06 | 41
K-Series Bar Joist-Angle Web [633121] | JKR-001-ISS-00222 | Name: K-Series Bar Joist-Angle Web [633121], PlacementId: K-Series Bar Joist-Angle Web [633121], TypeId: 16K6, Location: L3 TOS, EstimatedCost: 0 | L3 TOS | 19 | Open | Open | 23 | 16K6 | Location | K-Series Bar Joist-Angle Web [633121] | 2025-11-19 | 2025-11-19 | 32
System Panel [367301] | JKR-001-ISS-00101 | Name: System Panel [367301], PlacementId: System Panel [367301], TypeId: INT DARK, Location: , EstimatedCost: 0 | undefined | 19 | Open | Open | 17 | INT DARK | Location | System Panel [367301] | 2025-11-19 | 2025-11-19 | 32
System Panel [1055387] | JKR-001-ISS-1055387 | Name: System Panel [1055387], PlacementId: System Panel [1055387], TypeId: Solar Wall Edges, Location: , EstimatedCost: 0 | undefined | 19 | Approved | Approved | 17 | Solar Wall Edges | Location | System Panel [1055387] | 2025-11-24 | 2025-11-24 | -
CP_Solar Panel [1055186] | JKR-001-ISS-10551861 | Name: CP_Solar Panel [1055186], PlacementId: CP_Solar Panel [1055186], TypeId: Square, Location: , EstimatedCost: 0 | undefined | 19 | Open | Open | 17 | Square | Location | CP_Solar Panel [1055186] | 2025-11-25 | 2025-11-25 | 28
Floor [727212] | JKR-001-ISS-727212 | Issue regarding Floor [727212], identified as NW Concrete on Metal Deck, requires attention. The placement, also Floor [727212], has a root cause related to its location at R2 TOS. Payment approval for this item should be withheld until the issue is fully resolved. The estimated cost for rectification is currently zero. | R2 TOS | 19 | Open | Open | 23 | NW Concrete on Metal Deck | Location | Floor [727212] | 2025-11-25 | 2025-11-25 | 28
W Shapes-Column [608226] | JKR-001-ISS-6082262 | Name: W Shapes-Column [608226], PlacementId: W Shapes-Column [608226], TypeId: W14x109, Location: L1_37_Med, EstimatedCost: 0 | L1_37_Med | 19 | Open | Open | 17 | W14x109 | Location | W Shapes-Column [608226] | 2025-11-27 | 2025-11-27 | 26
K-Series Bar Joist-Angle Web [769881] | JKR-001-ISS-03478 | Name: K-Series Bar Joist-Angle Web [769881], PlacementId: K-Series Bar Joist-Angle Web [769881], TypeId: 16K6, Location: L2 TOS, EstimatedCost: 0 | L2 TOS | 19 | Open | Open | 110 | 16K6 | Location | K-Series Bar Joist-Angle Web [769881] | 2025-11-28 | 2025-11-28 | 25
Concrete-Rectangular-Column [608226]a | JKR-001-ISS-6082263 | Name: Concrete-Rectangular-Column [608226]a, PlacementId: Concrete-Rectangular-Column [608226], TypeId: 12x18, Location: L1_37_Med, EstimatedCost: 0 | L1_37_Med | 19 | Open | Open | 23 | 12x18 | Location | Concrete-Rectangular-Column [608226] | 2025-12-07 | 2025-12-07 | 20
Floor [726678] | JKR-001-ISS-726678 | A payment hold is required for the issue identified as Floor [726678], concerning the NW Concrete on Metal Deck. This issue is located at R2, with the root cause attributed to the location itself. The estimated cost associated with this particular problem is currently zero, and further action regarding payment release is suspended. | R2 | 19 | Open | Open | 23 | NW Concrete on Metal Deck | Location | Floor [726678] | 2025-12-08 | 2025-12-08 | 19
W Shapes-Column [608225] | JKR-001-ISS-12345a | An issue has been identified concerning W Shapes-Column [608225], specifically a W14x109 type, located at L1_37_Med. The root cause is attributed to its location, necessitating a review of potential design or placement discrepancies. An estimated cost of 500 has been noted, requiring further assessment regarding any change in price. | L1_37_Med | 19 | Open | Open | 23 | W14x109 | Location | W Shapes-Column [608225] | 2025-12-08 | 2025-12-08 | 19
W Shapes-Column [608224]1 | JKR-001-ISS-6082241 | The issue concerns W Shapes-Column [608224]1, identified as a W14x109 type. The column's placement, also W Shapes-Column [608224], is incorrectly located at L1_37_Med. The root cause has been determined as a location error, with an estimated cost of 0. | L1_37_Med | 19 | Open | Open | 23 | W14x109 | Location | W Shapes-Column [608224] | 2025-12-08 | 2025-12-08 | 19
Basic Wall [935927] | JKR-001-ISS-9359271 | Name: Basic Wall [935927], PlacementId: Basic Wall [935927], TypeId: Concrete 24", Location: L1_43_High, EstimatedCost: 0 | L1_43_High | 19 | Open | Open | 23 | Concrete 24" | Location | Basic Wall [935927] | 2025-12-10 | 2025-12-10 | 17
W Shapes-Column [643097] | JKR-001-ISS-643097 | A critical issue exists with W Shapes-Column [643097], a W10x49 type, located at L3. The root cause is identified as its placement. A hold payment is recommended due to this discrepancy, with an estimated cost of 100. Immediate attention is required to rectify this location-based issue. | L3 | 19 | Approved | Approved | 23 | W10x49 | Location | W Shapes-Column [643097] | 2025-12-12 | 2025-12-12 | -
Basic Wall [935927]1 | JKR-001-ISS-935927a | The issue pertains to Basic Wall [935927]1, a Concrete 24" type, placed at L1_43_High. The root cause is identified as its location. Resolution is required before payment can be processed, with an estimated cost of 50. | L1_43_High | 19 | Open | Open | 23 | Concrete 24" | Location | Basic Wall [935927] | 2025-12-12 | 2025-12-12 | 15
Threshold not inserted at door entrances | JKR-001-ISS-00125 | Threshold not inserted at door entrances | Flat 101 | 19 | Open | Open | 23 | Tile | Lack of painter | Main entrance of house | 2025-12-16 | 2025-12-19 | 10
Basic Wall [586648] | JKR-001-ISS-586648a1 | Hold the paymnt; Name: Basic Wall [586648], PlacementId: Basic Wall [586648], TypeId: Concrete 12", Location: L1_43_High, EstimatedCost: 100 | L1_43_High | 19 | Open | Open | 17 | Concrete 12" | Location | Basic Wall [586648] | 2025-12-18 | 2025-12-18 | 11